## Sheet1
Question | Question_label | Answer | Score | IsConcern | Checklist_Section | Issue_Reported | Rank
S.m.1 | S.m.1 Does the project have a “causal pathway” (i.e., theory of change, logic model, logframe, results framework, etc.) that explains how program activities lead to short-term and long-term outcomes? | 1 | 1 | Yes | Project Startup-MEL | No causal pathway / theory of change | 1
S.m.1.1 | S.m.1.1 If YES: Has the causal pathway been shared with the project team and partners / subawardees? | 1 | 1 | No | Project Startup-MEL | Causal pathway not shared | 2
S.m.2 | S.m.2 Does the project have a robust MEL plan that describes how the project will collect, analyze, report, and use data to track progress and assess effectiveness? | 1 | 1 | Yes | Project Startup-MEL | The project lacks a MEL plan. | 3
S.m.2.1 | S.m.2.1 If YES: Does the MEL plan have a table of indicators for program monitoring? | 1 | 1 | No | Project Startup-MEL | MEL plan missing indicator table | 4
S.m.2.2 | S.m.2.2 IF YES: Does the MEL plan have priority questions for program evaluation? | 1 | 1 | No | Project Startup-MEL | MEL plan missing evaluation questions | 5
S.m.2.3 | S.m.2.3 IF YES: Does the MEL plan have a learning agenda for program learning | 1 | 1 | No | Project Startup-MEL | MEL plan missing learning agenda | 6
S.m.2.4 | S.m.2.4 If YES: Has the project’s MEL plan been approved by the donor? | 1 | 1 | No | Project Startup-MEL | The MEL plan has not been approved by the donor. | 7
S.m.3 | S.m.3 Does the project have indicators that need to be reported to the donor? | 1 | 1 | No | Project Startup-MEL | Donor indicators not defined | 8
S.m.3.1 | S.m.3.1 If YES: Do all indicators have clearly documented operational definitions, data sources, calculation methodologies, and reporting frequencies? | 1 | 1 | Yes | Project Startup-MEL | Indicator definitions / sources incomplete | 9
S.m.3.2 | S.m.3.2 If YES: Do all indicators have targets? | 1 | 1 | No | Project Startup-MEL | Indicator targets missing | 10
S.m.3.3 | S.m.3.3 If YES: Have data collection tools been developed? | 1 | 1 | No | Project Startup-MEL | Data collection tools not developed | 11
S.m.4 | S.m.4 Does the project have a Data Quality Assurance (DQA) plan? | 1 | 1 | No | Project Startup-MEL | The project has no Data Quality Assurance (DQA) plan. | 12
S.m.4.1 | S.m.4.1 If YES: Does the DQA plan include practical tools and procedures such as routine data quality checklists, data quality guides, etc.? | 1 | 1 | No | Project Startup-MEL | DQA plan missing tools / procedures | 13
S.m.4.2 | S.m.4.2 If YES: Does the DQA plan describe how data quality issues will be addressed and prevented going forward? | 1 | 1 | No | Project Startup-MEL | DQA plan missing corrective actions | 14
S.m.5 | S.m.5 Has the project been registered in Pathfinder’s DHIS2 instance? | 1 | 1 | Yes | Project Startup-MEL | The project is not registered on DHIS2. | 15
S.m.5.1 | S.m.5.1 If YES: Are required data elements and indicators configured in DHIS2 to allow the project to begin reporting? | 1 | 1 | No | Project Startup-MEL | DHIS2 configuration incomplete | 16
S.m.5.2 | S.m.5.2 If YES: Have relevant staff been oriented and trained on how to enter data into and use DHIS2 for this project? | 1 | 1 | No | Project Startup-MEL | DHIS2 training not completed | 17
S.m.6 | S.m.6 Is the project conducting or planning any activities that require primary data collection (i.e., baseline survey, health facility assessments, etc)? | 1 | 1 | No | Project Startup-MEL | Primary data collection planned but not prepared | 18
S.m.6.1 | S.m.6.1 If YES: Has an activity plan been submitted for Pathfinder’s internal Human Subjects Research (HSR) review and determination? | 1 | 1 | No | Project Startup-MEL | HSR review not submitted | 19
S.m.7 | S.m.7 Are project partners / subawardees responsible for collecting project data? | 1 | 1 | No | Project Startup-MEL |  | 20
S.m.7.1 | S.m.7.1 If YES: Have project partners / subawardees been oriented on indicator definitions, data collection tools, data quality standards, and reporting flows and timelines? | 1 | 1 | No | Project Startup-MEL | Partners not oriented on data requirements | 21
S.m.8 | S.m.8 Do you have any MEL concerns with the project? | 0 | 1 | Yes | Project Startup-MEL | MEL concerns are present. | 22
S.m.8.1 | S.m.8.1 If YES: Please specify any MEL risks or concerns that may be affecting the project. | 0 | 1 | Yes | Project Startup-MEL | MEL risks / concerns present | 23
S.p.1 | S.P.1 Have new project staff been recruited to this project? | 1 | 1 | No | Project Startup-Programmatic | New project staff not recruited | 24
S.p.1.1 | S.P.1.1 If YES: Have new staff completed their onboarding orientation? | 1 | 1 | No | Project Startup-Programmatic | New staff onboarding not completed | 25
S.p.2 | S.P.2 Does the project have a workplan that describes key objectives, deliverables, and timelines? | 1 | 1 | Yes | Project Startup-Programmatic | Workplan missing objectives / deliverables / timelines | 26
S.p.2.1 | S.p.2.1 If YES: Have key risks and challenges that could affect early implementation been identified and documented in your workplan? | 1 | 1 | No | Project Startup-Programmatic | Key risks not identified / documented | 27
S.p.2.2 | S.p.2.2 If YES: Have roles and ownership for each major deliverable been clearly assigned in your workplan? | 1 | 1 | No | Project Startup-Programmatic | Roles / ownership not clearly assigned | 28
S.p.2.3 | S.p.2.3 If YES: Are activities sequenced in a logical order and aligned with the approved budget and staffing plan in your work plan? | 1 | 1 | No | Project Startup-Programmatic | Workplan activities not logically sequenced / aligned | 29
S.p.2.4 | S.p.2.4 If YES: Has the donor approved your workplan? | 1 | 1 | No | Project Startup-Programmatic | The workplan has not been approved by the donor. | 30
S.p.2.4.1 | S.p.2.4.1 If YES: Has the approved workplan been uploaded to the project shared folder? | 1 | 1 | No | Project Startup-Programmatic | Approved workplan not uploaded | 31
S.p.2.4.2 | S.p.2.4.2 If YES: Has the approved workplan been shared with project staff? | 1 | 1 | No | Project Startup-Programmatic | Workplan not shared with staff | 32
S.p.2.4.3 | S.p.2.4.3 If YES: Has the approved workplan been shared with relevant partners? | 1 | 1 | No | Project Startup-Programmatic | Workplan not shared with partners | 33
S.p.3 | S.p.3 Have project kick-off meetings been conducted with key stakeholders? | 1 | 1 | No | Project Startup-Programmatic | Kick-off meetings not conducted | 34
S.p.3.1 | S.p.3.1 If YES: Has the project leadership met with government counterparts? | 1 | 1 | No | Project Startup-Programmatic | No meeting with government counterparts | 35
S.p.3.1.1 | S.p.3.1.1 If YES: Has the project leadership discussed and confirmed alignment with national strategies, priorities, and guidelines? | 1 | 1 | No | Project Startup-Programmatic | Alignment with national strategies not confirmed | 36
S.p.3.2 | S.p.3.2 If YES: Has the project leadership met with implementing partners / subawardees? | 1 | 1 | No | Project Startup-Programmatic | No meeting with partners / subawardees | 37
S.p.3.2.1 | S.p.3.2.1 If YES: Have roles and responsibilities across Pathfinder and partners / subawardees been clearly defined and documented? | 1 | 1 | No | Project Startup-Programmatic | Roles / responsibilities not clearly defined | 38
S.p.3.3 | S.p.3.3 If YES: Has the project leadership met with stakeholders representing key beneficiaries? | 1 | 1 | No | Project Startup-Programmatic | No meeting with beneficiary stakeholders | 39
S.p.3.4 | S.p.3.4 If YES: Has the project leadership met with the donor? | 1 | 1 | No | Project Startup-Programmatic | No meeting with donor | 40
S.p.4 | S.p.4 Does the project have a clear reporting schedule for key deliverables? | 1 | 1 | Yes | Project Startup-Programmatic | No clear reporting schedule | 41
S.p.4.1 | S.p.4.1 If YES: Are all required donor deliverables and reporting frequencies clearly identified and understood by the project team? | 1 | 1 | No | Project Startup-Programmatic | Donor deliverables / frequencies unclear | 42
S.p.4.2 | S.p.4.2 If YES: Are reporting responsibilities clearly assigned, including who drafts, reviews, approves, and submits, for each key deliverable? | 1 | 1 | No | Project Startup-Programmatic | Reporting responsibilities not clearly assigned | 43
S.p.4.3 | S.p.4.3 If YES: Does the project have donor-approved templates for each key deliverable? | 1 | 1 | No | Project Startup-Programmatic | Donor-approved templates missing | 44
S.p.4.4 | S.p.4.4 If YES: Are subawardee and partner reporting timelines aligned with Pathfinder’s reporting deadlines? | 1 | 1 | No | Project Startup-Programmatic | Partner reporting timelines misaligned | 45
S.p.4.4.1 | S.p.4.4.1 IF YES: Have these timelines been clearly communicated to subawardees and partners? | 1 | 1 | No | Project Startup-Programmatic | Timelines not communicated to partners | 46
S.p.5 | S.p.5 Does the project have a communication / dissemination plan? | 1 | 1 | Yes | Project Startup-Programmatic | No communication plan is in place. | 47
S.p.5.1 | S.p.5.1 If YES: Does the project have branding guidelines? | 1 | 1 | No | Project Startup-Programmatic | Branding guidelines missing | 48
S.p.5.2 | S.p.5.2 If YES: Does the project have an external communication strategy? | 1 | 1 | No | Project Startup-Programmatic | No external communication strategy | 49
S.p.5.3 | S.p.5.3 If YES: Are roles and approval processes for external communications clearly understood by the project team? | 1 | 1 | No | Project Startup-Programmatic | Roles / approval processes unclear | 50
S.p.5.4 | S.p.5.4 If YES: Is there a clear timeline for when key external communication products should be released? | 1 | 1 | No | Project Startup-Programmatic | No clear timeline for external comms | 51
S.p.6 | S.p.6 Will the project need to procure goods or services? | 1 | 1 | No | Project Startup-Programmatic | Procurement needed but no plan | 52
S.p.6.1 | S.p.6.1 If YES: Has the project developed a procurement plan? | 1 | 1 | No | Project Startup-Programmatic | No procurement plan | 53
S.p.6.2 | S.p.6.2 If YES: Has the project established an inventory system using approved template for equipment/vehicles/furniture? | 1 | 1 | No | Project Startup-Programmatic | No inventory system | 54
S.p.6.3 | S.p.6.3 If YES: Have all project assets been procured? | 1 | 1 | No | Project Startup-Programmatic | Assets not procured | 55
S.p.6.4 | S.p.6.4 If YES: Does the project need to recruit consultants in this project? | 1 | 1 | No | Project Startup-Programmatic | Consultant recruitment needed | 56
S.p.6.4.1 | S.p.6.4.1 If YES: Have you developed the RFQs/RFPs? | 1 | 1 | No | Project Startup-Programmatic | RFQs/RFPs not developed | 57
S.p.6.4.2 | S.p.6.4.2 If YES: Have you selected your consultants? | 1 | 1 | No | Project Startup-Programmatic | Consultants not selected | 58
S.p.7 | S.p.7 Has the project budget been finalized? | 1 | 1 | No | Project Startup-Programmatic | Budget not finalized | 59
S.p.7.1 | S.p.7.1 If YES: Has the project budget been approved by the donor? | 1 | 1 | Yes | Project Startup-Programmatic | Budget not donor-approved | 60
S.p.7.2 | S.p.7.2 If YES: Does the project have a monthly budget to track burn rate during start-up? | 1 | 1 | No | Project Startup-Programmatic | No monthly budget for burn rate | 61
S.p.8 | S.p.8 Do you have any PROGRAMMATIC concerns with the project? | 0 | 1 | Yes | Project Startup-Programmatic | Programmatic concerns exist. | 62
S.p.8.1 | S.p.8.1 If YES: Please specify any programmatic risks or concerns that may be affecting the project. | 0 | 1 | Yes | Project Startup-Programmatic | Programmatic risks / concerns present | 63
I.m.1 | I.m.1 Does the project have a MEL plan? | 1 | 1 | Yes | Project Implementation-MEL | The project lacks a MEL plan. | 64
I.m.1.1 | I.m.1.1 If YES: Is the project implementing MEL activities outlined in the project’s MEL plan? | 1 | 1 | No | Project Implementation-MEL | MEL activities not implemented | 65
I.m.1.2 | I.m.1.2 If YES: Are MEL activities producing timely, usable data for reporting and to guide project implementation? | 1 | 1 | No | Project Implementation-MEL | MEL activities not producing usable data | 66
I.m.1.3 | I.m.1.3 If YES: Has the project made any adjustments to the MEL plan due to implementation realities? | 1 | 1 | No | Project Implementation-MEL | MEL plan not adjusted | 67
I.m.1.3.1 | I.m.1.3.1 If YES: Has the donor approved the revised MEL plan? | 1 | 1 | Yes | Project Implementation-MEL | The MEL plan has not been approved by the donor. | 68
I.m.2 | I.m.2 Is the project able to routinely and reliably report data on ALL indicators collected by the project? | 1 | 1 | Yes | Project Implementation-MEL | Unable to report data on all indicators | 69
I.m.2.1 | I.m.2.1 If YES: Are indicator data complete and submitted on time? | 1 | 1 | No | Project Implementation-MEL | Indicator data incomplete / late | 70
I.m.2.2 | I.m.2.2 If YES: Are indicator definitions, data sources, calculation methodologies, and reporting processes well understood by the MEL staff? | 1 | 1 | No | Project Implementation-MEL | Indicator definitions / processes unclear | 71
I.m.2.a | I.m.2.a If NO: Are reporting gaps understood and linked to specific causes that are being actively addressed? | 1 | 1 | No | Project Implementation-MEL | Reporting gaps not understood / addressed | 72
I.m.3 | I.m.3 Does the project have partners / subawardees that collect and report on project data? | 1 | 1 | No | Project Implementation-MEL |  | 73
I.m.3.1 | I.m.3.1 If YES: Are data submitted by partners / subawardees complete, on time, and in the correct format? | 1 | 1 | No | Project Implementation-MEL | Partner deliverables and reports are not delivered on time or are inaccurate. | 74
I.m.3.2 | I.m.3.2 If YES: Has the project reviewed the accuracy of data collected/submitted by partners/subawards? | 1 | 1 | No | Project Implementation-MEL | Partner data accuracy not reviewed | 75
I.m.3.3 | I.m.3.3 If YES: When data quality issues are identified, are feedback and/or capacity strengthening trainings provided to partners / subawardees as needed? | 1 | 1 | No | Project Implementation-MEL | No feedback / training to partners on data quality | 76
I.m.4 | I.m.4 Has the project implemented Data Quality Assurance (DQA) activities? | 1 | 1 | Yes | Project Implementation-MEL | DQA activities have not been implemented. | 77
I.m.4.1 | I.m.4.1 If YES: Are DQA activities conducted routinely and with rigor? | 1 | 1 | No | Project Implementation-MEL | DQA activities not routine / rigorous | 78
I.m.4.2 | I.m.4.2 If YES: Are DQA findings documented and used to assess confidence in the reported data? | 1 | 1 | No | Project Implementation-MEL | DQA findings not documented / used | 79
I.m.4.3 | I.m.4.3 If YES: Have any substantial data quality issues been identified? | 0 | 1 | No | Project Implementation-MEL | Substantial data quality issues present | 80
I.m.4.4 | I.m.4.4 If YES: Are recurring data quality issues being tracked to identify patterns or systemics issues? | 1 | 1 | No | Project Implementation-MEL | Recurring data quality issues not tracked | 81
I.m.4.5 | I.m.4.5 If YES: When data quality issues are identified, are appropriate mitigation actions agreed upon and taken? | 1 | 1 | No | Project Implementation-MEL | No mitigation for data quality issues | 82
I.m.5 | I.m.5 Is the project routinely reporting indicators / performance data into Pathfinder’s DHIS2? | 1 | 1 | Yes | Project Implementation-MEL | Routine DHIS2 reporting is not occurring. | 83
I.m.5.1 | I.m.5.1 If YES: Are data being entered into DHIS2 in a timely manner and in line with reporting requirements? | 1 | 1 | No | Project Implementation-MEL | DHIS2 data entry not timely / accurate | 84
I.m.5.2 | I.m.5.2 If YES: Have all data for previous reporting periods been fully entered into DHIS2 with no gaps? | 1 | 1 | No | Project Implementation-MEL | DHIS2 data incomplete (gaps) | 85
I.m.5.3 | I.m.5.3 If YES: Are DHIS2 dashboards being actively reviewed and used to track the project’s progress and identify performance gaps? | 1 | 1 | No | Project Implementation-MEL | DHIS2 dashboards not used for tracking | 86
I.m.6 | I.m.6 Does the project conduct routine data review meetings to guide project implementation? | 1 | 1 | Yes | Project Implementation-MEL | No routine data review meetings are being held. | 87
I.m.6.1 | I.m.6.1 If YES: Are indictor data reviewed against targets or expected performance? | 1 | 1 | No | Project Implementation-MEL | Data not reviewed against targets | 88
I.m.6.2 | I.m.6.2 If YES: Are decisions, course corrections, or follow-up actions explicitly identified based on the data reviewed? | 1 | 1 | No | Project Implementation-MEL | No decisions / actions from data review | 89
I.m.6.3 | I.m.6.3 If YES: Are notes from data review meetings compiled and disseminated? | 1 | 1 | No | Project Implementation-MEL | Data review notes not compiled | 90
I.m.6.4 | I.m.6.4 If YES: Are there project indicators where Pathfinder is currently underperforming? | 0 | 1 | No | Project Implementation-MEL | Underperforming indicators present | 91
I.m.6.4.1 | I.m.6.4.1 If YES: Have root causes of underperformance been analyzed, understood, and documented? | 1 | 1 | No | Project Implementation-MEL | Root causes of underperformance not analyzed | 92
I.m.6.4.2 | I.m.6.4.2 If YES: Have mitigation measures been put in place to address the underperformance? | 1 | 1 | No | Project Implementation-MEL | No mitigation for underperformance | 93
I.m.6.4.3 | I.m.6.4.3 If YES: Has the donor been informed on how Pathfinder is addressing underperformance in project indicators? | 1 | 1 | No | Project Implementation-MEL | Donor not informed about underperformance | 94
I.m.7 | I.m.7 Is the project conducting primary data collection activities (research studies/mid-term evaluation, etc)? | 1 | 1 | No | Project Implementation-MEL | Primary data collection not prepared | 95
I.m.7.1 | I.m.7.1 If YES, has an activity plan been submitted for Pathfinder’s internal Human Subjects Research (HSR) review and determination? | 1 | 1 | No | Project Implementation-MEL | HSR review not submitted | 96
I.m.8 | I.m.8 Has the project disseminated findings and learnings externally? | 1 | 1 | No | Project Implementation-MEL | Findings / learnings not disseminated | 97
I.m.9 | I.m.9 Do you have any MEL concerns with the project? | 0 | 1 | Yes | Project Implementation-MEL | MEL concerns are present. | 98
I.m.9.1 | I.m.9.1 If YES: Please specify any MEL risks or concerns that may be affecting the project. | 0 | 1 | Yes | Project Implementation-MEL | MEL risks / concerns present | 99
I.p.1 | I.p.1 Does the project have a donor-approved workplan guiding implementation? | 1 | 1 | Yes | Project Implementation-Programmatic | The workplan has not been approved by the donor. | 100
I.p.1.1 | I.p.1.1 If YES: Are project activities being implemented according to the workplan? | 1 | 1 | No | Project Implementation-Programmatic | Activities not following workplan | 101
I.p.1.2 | I.p.1.2 If YES: Are there emerging constraints affecting timelines, scope, or sequencing? | 1 | 1 | No | Project Implementation-Programmatic | Projects are facing emerging constraints that affect timelines and scope. | 102
I.p.2 | I.p.2 Has the project made any changes to the project workplan? | 1 | 1 | No | Project Implementation-Programmatic | Workplan changes not managed | 103
I.p.2.1 | I.p.2.1 If YES: Can the rationale for each change be clearly linked to implementation constraints, risk mitigation, or evidence collected from the project? | 1 | 1 | No | Project Implementation-Programmatic | Workplan changes lacking rationale | 104
I.p.2.2 | I.p.2.2 If YES: Have those changes been documented? | 1 | 1 | No | Project Implementation-Programmatic | Workplan changes not documented | 105
I.p.2.3 | I.p.2.3 If YES: Has the donor approved those changes? | 1 | 1 | No | Project Implementation-Programmatic | Workplan changes not donor-approved | 106
I.p.3 | I.p.3 Has the project submitted required donor reports? | 1 | 1 | No | Project Implementation-Programmatic | Donor reports not submitted | 107
I.p.3.1 | I.p.3.1 If YES: Have donor reports been submitted on time? | 1 | 1 | Yes | Project Implementation-Programmatic | Donor reports submitted late | 108
I.p.3.2 | I.p.3.2 If YES: Did the donor raise any substantive concerns or offer any negative feedback on the content or quality of the reports? | 0 | 1 | Yes | Project Implementation-Programmatic | The donor raised concerns about the report. | 109
I.p.3.2.1 | I.p.3.2.1 If YES: Were these concerns addressed and resolved in subsequent reports or follow-ups? | 1 | 1 | No | Project Implementation-Programmatic | Donor concerns not resolved | 110
I.p.3.3 | I.p.3.3 If YES: Were reports used internally for program learning and needed course corrections (rather than solely treated as a compliance exercise)? | 1 | 1 | No | Project Implementation-Programmatic | Reports not used for learning / course correction | 111
I.p.4 | I.p.4 Does the project hold regular team meetings to review the project’s progress, risks, and implementation challenges? | 1 | 1 | Yes | Project Implementation-Programmatic | No regular team meetings | 112
I.p.4.1 | I.p.4.1 If YES: Are these meetings used to surface issues, make decisions, and assign follow-up actions? | 1 | 1 | No | Project Implementation-Programmatic | Team meetings not used for issue resolution | 113
I.p.4.2 | I.p.4.2 If YES: Are partners/subawardees engaged in regular project meetings where implementation issues and deliverables are discussed? | 1 | 1 | No | Project Implementation-Programmatic | Partners not engaged in project meetings | 114
I.p.4.3 | I.p.4.3 If YES: Are government counterparts engaged routinely to provide updates, ensure alignment, and address any implementation issues? | 1 | 1 | No | Project Implementation-Programmatic | Government counterparts not engaged | 115
I.p.5 | I.p.5 Does the project receive deliverables or reports from partners/subawardees? | 1 | 1 | Yes | Project Implementation-Programmatic |  | 116
I.p.5.1 | I.p.5.1 If YES: Are deliverables / reports submitted on time? | 1 | 1 | No | Project Implementation-Programmatic | Partner deliverables / reports late | 117
I.p.5.2 | I.p.5.2 If YES: Do deliverables have complete information? | 1 | 1 | No | Project Implementation-Programmatic | Partner deliverables incomplete | 118
I.p.5.3 | I.p.5.3 If YES: Are the deliverables / reports satisfactory? | 1 | 1 | Yes | Project Implementation-Programmatic | Deliverables / reports not satisfactory | 119
I.p.5.3.1 | I.p.5.3.1 If NO: Is feedback and/or training provided to the partners / subawardees to correct deliverables that don’t meet expectations? | 1 | 1 | No | Project Implementation-Programmatic | No feedback / training to partners | 120
I.p.6 | I.p.6 Does the project have a communications / dissemination plan? | 1 | 1 | Yes | Project Implementation-Programmatic | No communication plan is in place. | 121
I.p.6.1 | I.p.6.1 IF YES: Is the project implementing the activities outlined in the communications / dissemination plan? | 1 | 1 | No | Project Implementation-Programmatic | Communications plan not implemented | 122
I.p.6.2 | I.p.6.2 If YES: Did the donor offer any positive feedback on the content or quality of the communication / dissemination activities? | 1 | 1 | No | Project Implementation-Programmatic | No donor positive feedback on comms | 123
I.p.7 | I.p.7 Is the project conducting monthly review of budget versus actuals? | 1 | 1 | Yes | Project Implementation-Programmatic | Monthly budget reviews are not taking place. | 124
I.p.7.1 | I.p.7.1 If YES: At the end of this reporting period, is cumulative project expenditure aligned with the approved budget? | 1 | 1 | No | Project Implementation-Programmatic | Expenditure not aligned with budget | 125
I.p.8 | I.p.8 Do you have any PROGRAMMATIC concerns with the project? | 0 | 1 | Yes | Project Implementation-Programmatic | Programmatic concerns exist. | 126
I.p.8.1 | I.p.8.1 If YES: Please specify any programmatic risks or concerns that may be affecting the project. | 0 | 1 | Yes | Project Implementation-Programmatic | Programmatic risks / concerns present | 127
c.m.1 | C.m.1 Is the project able to report data on ALL indicators collected by the project during the close-out phase? | 1 | 1 | Yes | Project Closeout-MEL | Unable to report all indicators during close-out | 128
c.m.1.a | C.m.1.a If NO: Are any missing indicators or reporting gaps documented with explanations? | 1 | 1 | No | Project Closeout-MEL | Missing indicators / reporting gaps not documented | 129
c.m.2 | C.m.2 Were project partners / subawardees responsible for collecting or reporting project data? | 1 | 1 | No | Project Closeout-MEL |  | 130
c.m.2.1 | C.m.2.1 If YES: Have partners / subawardees submitted project data on time? | 1 | 1 | No | Project Closeout-MEL | Partner deliverables and reports are not delivered on time or are inaccurate. | 131
c.m.2.2 | C.m.2.2 If YES: Has the project reviewed the accuracy of data collected/submitted by partners/subawardees? | 1 | 1 | No | Project Closeout-MEL | Partner data accuracy not reviewed | 132
c.m.2.3 | C.m.2.3 If YES: Does the project have all the data collected by partners/subawardees? | 1 | 1 | No | Project Closeout-MEL | Partner data missing | 133
c.m.2.4 | C.m.2.4 If YES: Have all data submitted by partners /subawardees been consolidated into a final project dataset? | 1 | 1 | No | Project Closeout-MEL | Partner data not consolidated | 134
c.m.3 | C.m.3 Has the project completed Data Quality Assurance (DQA) activities? | 1 | 1 | Yes | Project Closeout-MEL | DQA activities not completed | 135
c.m.4 | C.m.4 Have project indicators / performance data been fully entered into Pathfinder’s DHIS2? | 1 | 1 | Yes | Project Closeout-MEL | Data not fully entered into DHIS2 | 136
c.m.4.1 | C.m.4.1 If YES: Have the data been reported through the final project period? | 1 | 1 | No | Project Closeout-MEL | Data not reported for final period | 137
c.m.5 | C.m.5 Has the project completed a final data review meeting? | 1 | 1 | No | Project Closeout-MEL | No final data review meeting | 138
c.m.5.1 | C.m.5.1 If YES: Have performance of indicators been reviewed against targets? | 1 | 1 | No | Project Closeout-MEL | Indicator performance not reviewed | 139
c.m.5.2 | C.m.5.2 If YES: Have key findings and lessons learned been documented? | 1 | 1 | No | Project Closeout-MEL | Key findings / lessons not documented | 140
c.m.6 | C.m.6 Are there project indicators that are under performing? | 0 | 1 | Yes | Project Closeout-MEL | Underperforming indicators present | 141
c.m.6.1 | C.m.6.1 If YES: Are under performing indicators documented with explanations? | 1 | 1 | No | Project Closeout-MEL | Underperforming indicators not documented | 142
c.m.7 | C.m.7 Is the project conducting primary data collection activities during close out (endline survey, end of project evaluation, etc)? | 1 | 1 | No | Project Closeout-MEL | Primary data collection not prepared | 143
c.m.7.1 | C.m.7.1 If YES, has an activity plan been submitted for Pathfinder’s internal Human Subjects Research (HSR) review and determination? | 1 | 1 | No | Project Closeout-MEL | HSR review not submitted | 144
c.m.8 | C.m.8 Has the project disseminated findings externally? | 1 | 1 | Yes | Project Closeout-MEL | Findings not disseminated externally | 145
c.m.9 | C.m.9 Do you have any MEL concerns with the project? | 0 | 1 | Yes | Project Closeout-MEL | MEL concerns are present. | 146
c.m.9.1 | C.m.9.1 If YES: Please specify any MEL risks or concerns that may be affecting the project. | 0 | 1 | Yes | Project Closeout-MEL | MEL risks / concerns present | 147
c.p.1 | C.p.1 Have project activities been completed as per the workplan? | 1 | 1 | Yes | Project Closeout-Programmatic | Activities not completed as per workplan | 148
c.p.1.1 | C.p.1.1 If YES: Have any deviations from the work plan been documented and closed with the donor? | 1 | 1 | No | Project Closeout-Programmatic | Work plan deviations not documented / closed | 149
c.p.1.2 | C.p.1.2 If YES: Have responsibilities for ongoing or transitioned activities been formally handed over to partners or government representatives, where applicable? | 1 | 1 | No | Project Closeout-Programmatic | Handover not completed | 150
c.p.1.a | C.p1.a If NO: Do outstanding activities have agreed upon next steps and timelines? | 1 | 1 | No | Project Closeout-Programmatic | No plan for outstanding activities | 151
c.p.2 | C.p.2 Has the project submitted all deliverables to the donor? | 1 | 1 | Yes | Project Closeout-Programmatic | Deliverables not submitted | 152
c.p.2.1 | C.p.2.1 If YES: Have all project deliverables received donor approval or formal acknowledgement of receipt? | 1 | 1 | No | Project Closeout-Programmatic | Deliverables not donor-approved | 153
c.p.2.2 | C.p.2.2 If YES: Have all project deliverables been uploaded to Pathfinder's Award Deliverables Library? | 1 | 1 | No | Project Closeout-Programmatic | Deliverables not uploaded | 154
c.p.2.a | C.p.2.a If NO: Do outstanding deliverables have agreed upon next steps and timelines with the donor? | 1 | 1 | No | Project Closeout-Programmatic | No plan for outstanding deliverables | 155
c.p.3 | C.p.3 Has the project completed relevant dissemination / close-out events? | 1 | 1 | Yes | Project Closeout-Programmatic | Dissemination / close-out events not held | 156
c.p.4 | C.p.4 Have final project documents been properly filed within Pathfinder? | 1 | 1 | No | Project Closeout-Programmatic | Final documents not filed | 157
c.p.4.1 | C.p.4.1 If YES: Have final versions of key project documents been cleaned and stored in appropriate project folders? | 1 | 1 | No | Project Closeout-Programmatic | Final documents not stored properly | 158
c.p.4.2 | C.p.4.2 If YES: Have finalized tools, products, and learning outputs with broader relevance for Pathfinders been uploaded into Pathfinder Atlas? | 1 | 1 | No | Project Closeout-Programmatic | Tools / products not uploaded to Atlas | 159
c.p.5 | C.p.5 Has the project disseminated relevant documents / products? | 1 | 1 | Yes | Project Closeout-Programmatic | Documents / products not disseminated | 160
c.p.5.1 | C.p.5.1 If YES: Have final versions been shared with relevant stakeholders? | 1 | 1 | No | Project Closeout-Programmatic | Final versions not shared | 161
c.p.5.2 | C.p.5.2 If YES: Have final versions been uploaded on Pathfinder’s external website? | 1 | 1 | No | Project Closeout-Programmatic | Not uploaded externally | 162
c.p.6 | C.p.6 Is the project conducting monthly review of budget versus actuals? | 1 | 1 | Yes | Project Closeout-Programmatic | Monthly budget reviews are not taking place. | 163
c.p.6.1 | C.p.6.1 If YES: At the end of this reporting period, is cumulative project expenditure aligned with the approved budget? | 1 | 1 | No | Project Closeout-Programmatic | Expenditure not aligned with budget | 164
c.p.7 | C.p.7 Have all project assets (equipment, vehicles, materials) been accounted for, returned, or disposed of according to policy? | 1 | 1 | No | Project Closeout-Programmatic | Assets not accounted / returned / disposed | 165
c.p.7.a | C.p.7.a If NO: Is there a plan to address concerns related to project assets? | 1 | 1 | No | Project Closeout-Programmatic | No plan for asset concerns | 166
c.p.8 | C.p.8 Have all project agreements, contracts, consultancies, and/or vendor obligations been closed out / terminated according to the policy? | 1 | 1 | No | Project Closeout-Programmatic | Agreements / contracts not closed out | 167
c.p.8.a | C.p.8.a If NO: Is there a plan to address concerns related to procurement close out? | 1 | 1 | No | Project Closeout-Programmatic | No plan for procurement close out | 168
c.p.9 | C.p.9 Do you have any PROGRAMMATIC concerns with the project? | 0 | 1 | Yes | Project Closeout-Programmatic | Programmatic concerns exist. | 169
c.p.9.1 | C.p.9.1 IF YES: Please specify any programmatic risks or concerns that may be affecting the project. | 0 | 1 | Yes | Project Closeout-Programmatic | Programmatic risks / concerns present | 170

## Sheet2
Region | Country | Serenic Code | Project Title | Project Lead Name | QA Focal Person | Start Date | End Date | Amount | Funding Source | Technical Area | Kobo_Name
West & Central Africa | Burkina Faso | BF2501 | Strengthening Data Use for Impact in BF | Bruno Ki | Saturnin ZOETYANDE | 2025-10-21 | 2029-12-31 | 6500000 | Gates Foundation | Digital Health, Health Information Systems (HIS) Strengthening and Data Use for Primary Health Care Improvement | bf_gates_data_use_burkina_faso
West & Central Africa | Burkina Faso | MC2301 | Youth Champions for Climate Resilience in francophone West Africa (Multi Country) | Bruno Ki | Saturnin ZOETYANDE | 2023-06-01 | 2026-05-30 | 644107 | Fondation Chanel | Climate Resilience | mc_bf_fondchanel_youthchampions
West & Central Africa | Cote D'ivore | CI2501 | Accès Universel à la Contraception moderne en Côte d’Ivoire (AUCm-CI) | Yao konan Ernest | Moise TETCHI | 2025-06-26 | 2028-03-31 | 4170000 | Gates Foundation | Family planning | ci_universal_access_to_modern
West & Central Africa | Cote D'ivore | CI2401 | Accroître l’accès aux services de santé sexuelle et reproductive | Moïse Tetchi |  | 2024-05-02 | 2027-05-02 | 1500000 | William & Flora Hewlett Foundation |  | ci-accroître_l'accès_aux_services_de_san
West & Central Africa | Cote D'ivore | MC2301 | Youth Champions for Climate Resilience in Francophone West Africa (multi country project) | Bruno Ki | Ernest YAO | 2023-06-01 | 2026-05-31 | 348752 | Fondation CHANEL | Climate Resilience | mc_ci_fondchanel_youthchampions
West & Central Africa | DRC | CD2501 | Multisectoral Health and Nutrition Project – Family Planning, Complaints Management Mechanism, GBV/SEA-SH and Communication components – Kwilu province (WB) Project | Patrick Kabeya | Jackson Kipulu | 2025-06-01 | 2026-05-31 | 994767 | International Development Association | Family Planning | cd_sanru_fight_against_gbv__pmns_kwilu
West & Central Africa | DRC | CD2502 | Multisectoral Health and Nutrition Project – Family Planning, Complaints Management Mechanism, GBV/SEA-SH and Communication components – Kasai province (WB) Project | Patrick Kabeya | Saturnin Tumba | 2025-06-01 | 2026-05-31 | 854950 | International Development Association | Family Planning | cd_enabel_fight_against_gbvs_in_kasai___
West & Central Africa | DRC | CD2403 | Strengthening the Protective Environment for Women in Ituri Province Project (Pro-Femmes Ituri) | Jessé Mbusa | André Kabuyaya | 2024-12-21 | 2026-12-20 | 1230666 | Enabel | GBV | cd-strengthening the protective environm
West & Central Africa | DRC | CD2601 | PSI DISC Expansion in DRC project | Patrick Kabeya | Happy Katele | 2026-02-10 | 2027-04-30 | 1164375 | Gates Foundation (via PSI) | Family Planning | cd-psi disc expansion in drc project
East & Southern Africa | Ethiopia | ET2501 | COF-DMPA/SC/SI | Dr Ketsela | Teshager Mersha | 2025-02-14 | 2026-02-13 | 250000 | Clinton Health Access Initative | Family Planning | et-cof-dmpa/sc/si
East & Southern Africa | Ethiopia | ET2301 | Youth friendly services and community approaches to reach adolescents and youth. | Abebe Kassa | Teshager Mersha | 2023-10-31 | 2026-10-30 | 4100000 | Gates Foundation | Adoelscent and Youth Health | et_gates_yfs___community_approaches
East & Southern Africa | Ethiopia | ET1602 | Stanley Eisenburg Girls Education program | Abebe Kassa | Teshager Mersha | 2025-09-01 | 2029-08-01 | 2630000 | Stanley Eisenberg | Girls Education and SRH | et_stanley eisenburg girls education
SAMENA | India | IN2101 | RBBF – YUVAA Supplementary Project | Laxmi Rao |  | 2021-04-13 | 2026-03-31 | 100000 | Ramesh and Kalpana Bhatia Family Foundation |  | in_bhatiafoundation_yuvaa_supplement
SAMENA | Jordan | JO2101 | AWH 3 | Wejdan Abu Lail |  | 2023-08-01 | 2026-12-31 | 1374559 | Soderberg Foundation |  | jo_soderberg_livelihoo_jordan
SAMENA | Jordan | JO2401 | Improving Leadership & Employability of Underserved Populations | Anna White |  | 2024-08-01 | 2026-07-31 | 525000 | Soderberg Foundation |  | jo-improving leadership_employability
East & Southern Africa | Mozambique | MZ2402 | IMPACTO SF | Luc Van der Veken | Artur Sulemane | 2024-07-11 | 2031-03-30 | 14676921 | Global Affairs Canada | Gender Equity, SRHR including Family Planning, Abortion and VBG | mz-impacto sf
East & Southern Africa | Mozambique | MZ2501 | DISC-SC | Baltazar Chilundo | Luc Van der Veken | 2025-05-20 | 2027-03-31 | 350000 | PSI/Gates Fundation | Family planning focused on self injection | mz-disc-sc
East & Southern Africa | Mozambique | MZ2005 | Mas Escolha | Ivania Euadaba | Inocencia Fumo | 2024-03-21 | 2026-12-11 | 1856000 | Norwegian Embassy | SRHR including Family Planning, Abortion and VBG | mz-mas escolha
East & Southern Africa | Mozambique | MZ2001 | Hands Off! (CB FSW – Netherlands) | Arminda Zandamela | Artur Sulemane | 2020-01-01 | 2026-04-30 | 1812181 | AidsFonds/ Nederlands Embassy | Strenghening the National Sex Workers Rights Plataform in Mozambique to fostering access to inclusive services (Psychosocial, Health, Legal) | mz-hands off! (cb fsw – netherlands)
East & Southern Africa | Mozambique | MC2501 | FC2 | Arminda Zandamela | Amelia Pelembe | 2025-03-01 | 2026-02-28 | 94906 | Female Health Company | Family Planning and HIV prevention | mz-the fc2 multi-country project
East & Southern Africa | Mozambique | MZ2502 | Pre Introduction of Hormonal IUD | Joaquim Fernando | Baltazar Chilundo | 2025-10-01 | 2026-09-30 | 243747 | COF-CHAI/FCDO | Family Planning | mz-pre introduction of hormonal iud
East & Southern Africa | Mozambique | MZ2503 | Futures With Chioce - Inhambane | Inocencia Fumo | Baltazar | 2025-11-01 | 2026-12-31 | 1156136 | Irish Aid/ Irish Embassy | SRHR including Family Planning, Abortion and VBG | mz-futures with chioce - inhambane
West & Central Africa | Niger | NE2301 | Jagorantin MATASSA : Listen to Young People Program | Hassan Sanda Yacouba | Harouna Zakou | 2024-01-01 | 2027-12-31 | 12837840 | Dutch Ministry of Foreign Affairs/ Netherlands Development Cooperation | SRH, AYSRH | ne_dutch_government_j_matassa
West & Central Africa | Niger | MC2301 | Youth Champions for Climate Resilience in Francophone West Africa (multi country project) | Bruno Ki | Harouna Zakou | 2023-10-01 | 2026-05-31 | 387141 | Fondation CHANEL | Climate Resilience | mc_ne_fondchanel_youthchampions
West & Central Africa | Nigeria | NG2204 | Geospatial data/tools/tech for RMNCHN microplanning and decision support | Amina Dorayi | Dada Oluwasogo Kehinde | 2022-11-01 | 2026-04-30 | 3000000 | Gates Foundation | Digital Health for MNCH | ng-geospatial data/tools/tech for rmnchn
West & Central Africa | Nigeria | NG2403 | HPV Champions and Advocacy Engagement Project | Amina Dorayi | Dada Oluwasogo Kehinde | 2024-09-12 | 2026-05-30 | 400000 | Gates Foundation | Advocacy for HPV vaccination | ng-hpv champions and advocacy engagement
West & Central Africa | Nigeria | NG2405 | Task-Shifting/Sharing to Strengthen PHC Services in Kaduna and Kano | Amina Dorayi | Dada Oluwasogo Kehinde | 2024-10-09 | 2026-09-30 | 2500000 | Gates Foundation | Health system strengthening | ng_gates_task_shifting_to_strengthen_phc
West & Central Africa | Nigeria | NG2404 | Advocacy and implementation of MNCNH innovations in Nigeria | Amina Dorayi | Dada Oluwasogo Kehinde | 2024-09-01 | 2028-06-30 | 600000 | Gates Foundation | Advocacy | ng-advocacy and implementation of mncnh
West & Central Africa | Nigeria | NG2406 | Modelling to support Decision-Making for Cervical Cancer Prevention and Screening | Amina Dorayi | Dada Oluwasogo Kehinde | 2024-08-01 | 2027-07-31 | 161819 | Gates Foundation | Data use for decision making on HPV | ng-modelling to support decision-making
West & Central Africa | Nigeria | NG2407 | Accelerating the Expanded Adoption of RMNCH Innovations and Health Reforms. | Amina Dorayi | Dada Oluwasogo Kehinde | 2024-10-28 | 2027-12-31 | 1516139 | Gates Foundation | MNCH | ng_taconnect_rmnch_innovations___health_
West & Central Africa | Nigeria | NG2501 | SMART Advocacy for Strategic Action (SASA) Advocacy Initiative Capacity building | Amina Dorayi | Dada Oluwasogo Kehinde | 2024-11-14 | 2027-10-31 | 1020000 | Gates Foundation | PAC for FP/MNCH | ng-smart advocacy for strategic action
West & Central Africa | Nigeria | MC2501 | The FC2 Multi-country Project | Amina Dorayi | Dada Oluwasogo Kehinde | 2025-03-01 | 2026-06-30 | 76369 | Female Health Company | SRH | ng-the fc2 multi-country project
West & Central Africa | Nigeria | NG2503 | Supporting HPV vaccination champions in Nigeria | Amina Dorayi | Dada Oluwasogo Kehinde | 2025-08-19 | 2027-03-31 | 400000 | Gates Foundation | Champion building for HPV vaccination | ng-supporting hpv vaccination champions
West & Central Africa | Nigeria | NG2505 | Scaling RMNCNH Innovations in Humanitarian Settings | Amina Dorayi | Dada Oluwasogo Kehinde | 2025-10-31 | 2029-10-31 | 300000 | Gates Foundation | MNCH | ng-scaling rmncnh innovations in humanit
West & Central Africa | Nigeria | NG2504 | Community Access to RMNCAH+N Innovations and Services (CARMNIS) | Amina Dorayi | Dada Oluwasogo Kehinde | 2025-11-12 | 2029-10-31 | 12168048 | Gates Foundation | Community-based health intervention | ng-community access to rmncahn innovati
SAMENA | Pakistan | PK2203 | Strengthening Health Systems to Increase Access to Post-Pregnancy Family Planning – Qadam Ba Qadam | Zaib |  | 2022-06-29 | 2026-03-30 | 4597870 | Gates Foundation |  | pk-strengthening health systems to incre
SAMENA | Pakistan |  | World Bank Punjab Government – Community Health Inspectors Lot 1 (Lahore) | Zaib |  | 2025-11-01 | 2026-12-01 | 6114380 | World Bank Punjab Government |  | pk-world bank punjab government – commun
East & Southern Africa | Tanzania | TZ2202 | National Expansion of M-MAMA, the emergency transport for pregnant women and newborns in TZ | Steven Minja | Ediphonce Joseph | 2021-12-31 | 2027-03-30 | 11152885 | Vodafone Foundation | MNCH | tz-national expansion of m-mama, the eme
East & Southern Africa | Tanzania | TZ2304 | Bergstrom Maamuzi Yako-Kesho Yako Phase IV | Godbless Mtega | Ediphonce Joseph | 2023-12-31 | 2026-12-30 | 635000 | Erick E & Edith H Bergstrom Foundation | Family Planning | tz-bergstrom maamuzi yako-kesho yako pha
East & Southern Africa | Tanzania | TZ2501 | Prevention of Sexual Violence Against Children - KUWAZA Phase 4 | Ediphonce Joseph | Ediphonce Joseph | 2025-04-01 | 30/3/2027 | 1250000 | Oak Foundation | GBV | tz-prevention of sexual violence against
East & Southern Africa | Tanzania | TZ2402 | Promoting Integrated Health & Conservation Programing in Northern Tanzania Rangelands | Festo Komba | Ediphonce Joseph | 2024-06-30 | 2027-06-29 | 1000000 | Margaret A Cargill Foundation | Climate Resilience | tz-promoting integrated health & conserv
East & Southern Africa | Tanzania | TZ2403 | Scaling up family planning in TZ | Haikael Mandari | Ediphonce Joseph | 2024-08-31 | 2026-05-30 | 766139 | FCDO Via EngenderHealth | Family Planning | tz-scaling up family planning in tz
East & Southern Africa | Tanzania | TZ2404 | Advancing Reproductive Rights in TZ - Phase XII | Sitti Shio | Ediphonce Joseph | 2024-09-30 | 2027-09-29 | 600000 | CGD | Advocacy | tz-advancing reproductive rights in tz -
East & Southern Africa | Tanzania | TZ2405 | Increase access and use of quality cPAC and PPFP Services | Isihaka Mwandalima | Ediphonce Joseph | 2024-12-31 | 2026-12-30 | 250000 | Erick E & Edith H Bergstrom Foundation | CPAC & Family Planning | tz-increase access and use of quality cp
East & Southern Africa | Tanzania | TZ2502 | Integrating Population, Health and Environment (PHE) Efforts in the Katavi-Mahale Ecosystem and Corridor Conservation Projects (KAMACO) | Vedastus Mugeta | Ediphonce Joseph | 2025-10-01 | 30/08/2027 | 210000 | FZS through KFW | Climate Resilience & Health | tz-integrating population, health and en
East & Southern Africa | Tanzania | TZ2504 | Health, Empowerment & Rights (HER) Future | Haikael Mandari | Ediphonce Joseph | 2026-01-01 | 31/12/2028 | 4700000 | Royal Norweigan Embassy - Tanzania | AYSRH & CPAC | tz-health, empowerment & rights (her) fu
East & Southern Africa | Uganda | UG2501 | Empowering Women for Better Reproductive Health Outcomes -EMPOWER | Ritah Waddimba | Ronald Nabimara | 2025-02-02 | 2030-01-30 | 33827493 | Department for International Development | Maternal Child health/Family Plannning | ug_fcdo_empower_programme

## Issues
Question | Question_label | Answer | Score | IsConcern | Checklist_Section | Issue_Tracking
S.m.8.1 | S.m.8.1 If YES: Please specify any MEL risks or concerns that may be affecting the project. |  |  | Yes | Project Startup-MEL | Exists MEL risks/concerns at Project Startup
I.p.8.1 | I.p.8.1 If YES: Please specify any programmatic risks or concerns that may be affecting the project. |  |  | Yes | Project Implementation-Programmatic | Exists Programmatic risks/concerns at Project Implementation
I.m.9.1 | I.m.9.1 If YES: Please specify any MEL risks or concerns that may be affecting the project. |  |  | Yes | Project Implementation-MEL | Exists MEL risks/concerns at Project Implementation
c.p.9.1 | C.p.9.1 IF YES: Please specify any programmatic risks or concerns that may be affecting the project. |  |  | Yes | Project Closeout-Programmatic | Exists Programmatic risks/concerns at Project Closeout
c.m.9.1 | C.m.9.1 If YES: Please specify any MEL risks or concerns that may be affecting the project. |  |  | Yes | Project Closeout-MEL | Exists MEL risks/concerns at Project Closeout